## Julai 2026
Sistem | Sub-Sistem | Item | Deskripsi | Kekerapan | T01 | T02 | T03 | T04 | T05 | T06 | T07 | T08 | T09 | T10 | T11 | T12 | T13 | T14 | T15 | T16 | T17 | T18 | T19 | T20 | T21 | T22 | T23 | T24 | T25 | T26 | T27 | T28 | T29 | T30 | T31
1.0 Air Conditioning and Mechanical Ventilation System | 1.1.1 Plant Room | i. | General | W/M/6M | bar: T03; T10; T17; T23 to T24; T31
1.0 Air Conditioning and Mechanical Ventilation System | 1.1.1 Plant Room | ii. | Chillers (Water Cooled) | D/M/6M/Y | D | D | D |  |  | D | D | D | D | D |  |  | D | D | D | D | D |  |  | D | D | D | D, M | D |  |  | D | D | D | D | D
1.0 Air Conditioning and Mechanical Ventilation System | 1.1.1 Plant Room | iii. | Chillers (Air Cooled Chiller System) | D/M/6M/Y | D | D | D |  |  | D | D | D | D | D |  |  | D | D | D | D | D |  |  | D | D | D | D, M | D |  |  | D | D | D | D | D
1.0 Air Conditioning and Mechanical Ventilation System | 1.1.1 Plant Room | iv. | Pumps | M | T23: D, M
1.0 Air Conditioning and Mechanical Ventilation System | 1.1.1 Plant Room | v. | Electric Motors | M/3M | bar: T23
1.0 Air Conditioning and Mechanical Ventilation System | 1.1.1 Plant Room | vi. | Electrical Switchboard/ Control Panel | M | bar: T28
1.0 Air Conditioning and Mechanical Ventilation System | 1.1.2 Heat Exchanger Plant Room | 1.1.2 | Heat Exchanger Plant Room | M/3M | bar: T28
1.0 Air Conditioning and Mechanical Ventilation System | 1.1.3 Cooling Towers | 1.1.3 | Cooling Towers | D/M | D | D | D |  |  | D | D | D | D | D |  |  | D | D | D | D | D |  |  | D | D | D, M | D | D |  |  | D | D | D | D | D
1.0 Air Conditioning and Mechanical Ventilation System | 1.1.4 Chilled Water Storage & Expansion Tank | 1.1.4 | Chilled Water Storage & Expansion Tank | W/M/Y | bar: T03; T10; T16 to T17; T24; T31
1.0 Air Conditioning and Mechanical Ventilation System | 1.1.5 Air Handling Units and Fan-Coils | 1.1.5 | Air Handling Units and Fan-Coils | M/3M/6M/Y | bar: T16
1.0 Air Conditioning and Mechanical Ventilation System | 1.1.6 Ducting, Grilles and Dampers | 1.1.6 | Ducting, Grilles and Dampers | M/6M | bar: T16; T27
1.0 Air Conditioning and Mechanical Ventilation System | 1.1.7 The Perfomance of The Complete Ventilation, Pressurization, Exhaust and Smoke Spill System | 1.1.7 | The Perfomance of The Complete Ventilation, Pressurization, Exhaust and Smoke Spill System | M/6M | bar: T16; T27
1.0 Air Conditioning and Mechanical Ventilation System | 1.4.1 Evaporator (Cooling Unit) | 1.4.1 | Evaporator (Cooling Unit) | D/M/Y | D | D | D |  |  | D | D | D | D | D |  |  | D | D | D | D | D |  |  | D | D | D, M | D | D |  |  | D | D | D | D | D
1.0 Air Conditioning and Mechanical Ventilation System | 1.4.2 Condenser | 1.4.2 | Condenser | M/Y | bar: T22
1.0 Air Conditioning and Mechanical Ventilation System | 1.4.3 Electrical Switchboard / Control Panel | 1.4.3 | Electrical Switchboard / Control Panel | M | bar: T22
1.0 Air Conditioning and Mechanical Ventilation System | 1.5.1 Evaporator / Condensor | 1.5.1 | Evaporator / Condensor | M/Y | bar: T24
1.0 Air Conditioning and Mechanical Ventilation System | 1.5.2 Electrical Switchboard / Control Panel | 1.5.2 | Electrical Switchboard / Control Panel | M/Y | bar: T24
1.0 Air Conditioning and Mechanical Ventilation System | 1.6 Piping and Fittings (Expose and Accessable) | 1.6 | Piping and Fittings (Expose and Accessable) | M/6M | bar: T24; T27
1.0 Air Conditioning and Mechanical Ventilation System | 1.7 Painting | 1.7 | Painting | Y
2.0 Fire Fighting System |  | 2.1 | General | D/6M/Y | bar: T01 to T03; T06 to T10; T13 to T17; T20 to T24; T27 to T31
2.0 Fire Fighting System | 2.2.1 Pump Room | 2.2.1 | Pump Room | W/M/6M | T02: W; T09: W; T14: M; T16: W; T23: W; T30: W; T31: 6M
2.0 Fire Fighting System | 2.2.2 Tank | 2.2.2 | Tank | W/M/6M/Y | T02: W; T09: W; T14: M; T16: W; T23: W; T30: W; T31: 6M
2.0 Fire Fighting System | 2.2.3 Pumps (General) | i. | General | M | bar: T14
2.0 Fire Fighting System | 2.2.3 Pumps (General) | ii. | Control Panel | M | bar: T14
2.0 Fire Fighting System | 2.2.4 Piping and Fittings | 2.2.4 | Piping and Fittings | M/6M | bar: T14; T31
2.0 Fire Fighting System | 2.2.5 Landing, Valves, Hose Reel Drums, Cradles, Hoses, Nozzles, etc. | 2.2.5 | Landing, Valves, Hose Reel Drums, Cradles, Hoses, Nozzles, etc. | M | bar: T14
2.0 Fire Fighting System | 2.2.6 Sprinkler System | 2.2.6 | Sprinkler System | M | bar: T14
2.0 Fire Fighting System | 2.2.7 Breeching Inlet | 2.2.7 | Breeching Inlet | M | bar: T14
2.0 Fire Fighting System | 2.3 Fire Detection and Alarm System | 2.3 | Fire Detection and Alarm System | D/M/6M | D | D | D |  |  | D | D | D | D | D |  |  | D | D | D, M | D | D |  |  | D | D | D | 6M, D | D |  |  | D | D | D | D | D
2.0 Fire Fighting System | 2.4.1 Panel | 2.4.1 | Panel | M | bar: T15
2.0 Fire Fighting System | 2.4.2 Battery | 2.4.2 | Battery | M | bar: T15
2.0 Fire Fighting System | 2.4.3 Automatic Control | 2.4.3 | Automatic Control | M | bar: T15
2.0 Fire Fighting System | 2.4.4 Electrical | 2.4.4 | Electrical | M | bar: T15
2.0 Fire Fighting System | 2.4.5 Handsets | 2.4.5 | Handsets | M | bar: T15
2.0 Fire Fighting System | 2.4.6 General | 2.4.6 | General | M | bar: T15
2.0 Fire Fighting System | 2.5.1 Cylinder, Hoses, Canister, etc. | 2.5.1 | Cylinder, Hoses, Canister, etc. | M | bar: T15
2.0 Fire Fighting System | 2.5.2 Pilot Cylinder | 2.5.2 | Pilot Cylinder | M | bar: T15
2.0 Fire Fighting System | 2.5.3 Panel | 2.5.3 | Panel | M | bar: T15
2.0 Fire Fighting System | 2.5.4 Devices | 2.5.4 | Devices | M/3M/6M | T15: M; T22: 3M; T23: 6M
2.0 Fire Fighting System | 2.5.5 Aerohub | 2.5.5 | Aerohub | M/6M | bar: T15; T23
2.0 Fire Fighting System | 2.6 Portable Fire Extinguisher | 2.6 | Portable Fire Extinguisher | M | bar: T15
2.0 Fire Fighting System | 2.7 BOMBA Link (SPKA) | 2.7 | BOMBA Link (SPKA) | M | bar: T15
2.0 Fire Fighting System | 2.8.1 General | 2.8.1 | General | M/Y | bar: T13
2.0 Fire Fighting System | 2.8.2 Pump Room | 2.8.2 | Pump Room | M | bar: T13
2.0 Fire Fighting System | 2.8.3 Tank | 2.8.3 | Tank | M/3M/6M/Y | T13: M; T17: 3M; T22: 6M
2.0 Fire Fighting System | 2.8.4 Piping and Fitting | 2.8.4 | Piping and Fitting | M | bar: T13
2.0 Fire Fighting System | 2.8.5 Pump & Motor | 2.8.5 | Pump & Motor | M | bar: T13
2.0 Fire Fighting System | 2.9 Painting | 2.9 | Painting | 6M | bar: T22
3.0 LIFT |  | 3.1 | Motor Room | M | bar: T09
3.0 LIFT | 3.2 Hoist Way | 3.2 | Hoist Way | M | bar: T09
3.0 LIFT | 3.3 Lift Car | 3.3 | Lift Car | M /5Y | bar: T09
3.0 LIFT | 3.4 Entrance | 3.4 | Entrance | M | bar: T09
3.0 LIFT | 3.5 Lift Pit | 3.5 | Lift Pit | M | bar: T09
3.0 LIFT | 3.6 Automatic Rescue Device (ARD) | 3.6 | Automatic Rescue Device (ARD) | M | bar: T09
3.0 LIFT | 3.7 Building Control Room | 3.7 | Building Control Room | M | bar: T09
3.0 LIFT | 3.8 VIP Lift Access System | 3.8 | VIP Lift Access System | M | bar: T09
4.0 GONDOLA |  | 4.1 | Maintenance | M | bar: T08
5.0 Cold Water Supply and Booster Pump-Pump Room |  | 5.1 | Pump room | W/M/6M | T01: W; T08: W; T15: W; T17: M; T22: W; T24: 6M; T29: W
5.0 Cold Water Supply and Booster Pump-Pump Room | 5.2 Tanks (Suction & Storage) | 5.2 | Tanks (Suction & Storage) | M/6M | bar: T17; T24
5.0 Cold Water Supply and Booster Pump-Pump Room | 5.3 Pumps | i. | General | M | bar: T17
5.0 Cold Water Supply and Booster Pump-Pump Room | 5.3 Pumps | ii. | Control Panel | M | bar: T17
5.0 Cold Water Supply and Booster Pump-Pump Room | 5.4 Piping & Fitting | 5.4 | Piping & Fitting | M/6M | bar: T17; T24
5.0 Cold Water Supply and Booster Pump-Pump Room | 5.5 Pressure Vessel | 5.5 | Pressure Vessel | M | bar: T17
5.0 Cold Water Supply and Booster Pump-Pump Room | 5.6 Submersible Pumps | 5.6 | Submersible Pumps | W/M | bar: T01; T08; T15; T17; T22; T29
5.0 Cold Water Supply and Booster Pump-Pump Room | 5.7 Painting | 5.7 | Painting | 6M | bar: T24
6.0 Inspection of Mechanical Services Above Ceiling |  | 6 | Inspection of Mechanical Services Above Ceiling | 6M | bar: T28
7.0 Kitchen Equipment |  | 7 | Kitchen Equipment | 3M | bar: T21
7.0 Kitchen Equipment | 7.1 Open Burner Range | 7.1 | Open Burner Range | M/3M | bar: T10; T21
7.0 Kitchen Equipment | 7.2 Hobs | 7.2 | Hobs | M | bar: T10
7.0 Kitchen Equipment | 7.3 Kitchen Hood | 7.3 | Kitchen Hood | W/M | bar: T01; T08; T10; T15; T22; T29
7.0 Kitchen Equipment | 7.4 Kitchen Exhaust Fan | 7.4 | Kitchen Exhaust Fan | M/6M/Y | bar: T10; T30
8.0 Irrigation System and Landscape |  | 8.1 | Water pump | M/3M/Y | bar: T14; T17
8.0 Irrigation System and Landscape | 8.2 Electrical Motor | 8.2 | Electrical Motor | M/3M/6M | T14: M; T17: 3M; T30: 6M
8.0 Irrigation System and Landscape | 8.3 Electrical Switchboard / Control Panel | 8.3 | Electrical Switchboard / Control Panel | M/6M | bar: T14; T30
8.0 Irrigation System and Landscape | 8.4 Piping | 8.4 | Piping | M | bar: T14
8.0 Irrigation System and Landscape | 8.5 Filter | 8.5 | Filter | M | bar: T14
8.0 Irrigation System and Landscape | 8.6 Skimmer | 8.6 | Skimmer | M | bar: T14
9.0 Other Mechanical Equipment System |  | i. | Operation | M | bar: T09
9.0 Other Mechanical Equipment System |  | ii. | Maintenance | M | bar: T09
9.0 Other Mechanical Equipment System | 9.1 Roller Shutter / Fire Roller Shutter | i. | General | M | bar: T09
9.0 Other Mechanical Equipment System | 9.1 Roller Shutter / Fire Roller Shutter | ii. | Electric Motors | M | bar: T09
9.0 Other Mechanical Equipment System | 9.1 Roller Shutter / Fire Roller Shutter | iii. | Electrical Switchboard / Control Panel | M | bar: T09
9.0 Other Mechanical Equipment System | 9.2 Hand Dryer | 9.2 | Hand Dryer | W/M | bar: T01; T06; T09; T13; T20; T27
9.0 Other Mechanical Equipment System | 9.3 Grey Water Harvesting System | i. | General | W/M | bar: T01; T06; T09; T13; T20; T27
9.0 Other Mechanical Equipment System | 9.4 Rain Water Harvesting System | i. | General | W/M | bar: T01; T06; T09; T13; T20; T27
9.0 Other Mechanical Equipment System | 9.4 Rain Water Harvesting System | ii. | Control Panel | M | bar: T09

## Ogos 2026
Sistem | Sub-Sistem | Item | Deskripsi | Kekerapan | T01 | T02 | T03 | T04 | T05 | T06 | T07 | T08 | T09 | T10 | T11 | T12 | T13 | T14 | T15 | T16 | T17 | T18 | T19 | T20 | T21 | T22 | T23 | T24 | T25 | T26 | T27 | T28 | T29 | T30 | T31
1.0 Air Conditioning and Mechanical Ventilation System | 1.1.1 Plant Room | i. | General | W/M/6M | bar: T03; T07; T14; T21; T24; T28
1.0 Air Conditioning and Mechanical Ventilation System | 1.1.1 Plant Room | ii. | Chillers (Water Cooled) | D/M/6M/Y |  |  | D | D | D | D | D |  |  | D | D | D | D | D |  |  | D | D | D | D | D |  |  | D, M |  | D | D | D
1.0 Air Conditioning and Mechanical Ventilation System | 1.1.1 Plant Room | iii. | Chillers (Air Cooled Chiller System) | D/M/6M/Y |  |  | D | D | D | D | D |  |  | D | D | D | D | D |  |  | D | D | D | D | D |  |  | D, M |  | D | D | D
1.0 Air Conditioning and Mechanical Ventilation System | 1.1.1 Plant Room | iv. | Pumps | M | T24: D, M
1.0 Air Conditioning and Mechanical Ventilation System | 1.1.1 Plant Room | v. | Electric Motors | M/3M | bar: T24
1.0 Air Conditioning and Mechanical Ventilation System | 1.1.1 Plant Room | vi. | Electrical Switchboard/ Control Panel | M | bar: T28
1.0 Air Conditioning and Mechanical Ventilation System | 1.1.2 Heat Exchanger Plant Room | 1.1.2 | Heat Exchanger Plant Room | M/3M | bar: T28
1.0 Air Conditioning and Mechanical Ventilation System | 1.1.3 Cooling Towers | 1.1.3 | Cooling Towers | D/M |  |  | D | D | D | D | D |  |  | D | D | D | D | D |  |  | D | D | D | D | D |  |  | D, M |  | D | D | D
1.0 Air Conditioning and Mechanical Ventilation System | 1.1.4 Chilled Water Storage & Expansion Tank | 1.1.4 | Chilled Water Storage & Expansion Tank | W/M/Y | bar: T03; T07; T14; T17; T21; T28
1.0 Air Conditioning and Mechanical Ventilation System | 1.1.5 Air Handling Units and Fan-Coils | 1.1.5 | Air Handling Units and Fan-Coils | M/3M/6M/Y | bar: T17
1.0 Air Conditioning and Mechanical Ventilation System | 1.1.6 Ducting, Grilles and Dampers | 1.1.6 | Ducting, Grilles and Dampers | M/6M | bar: T17
1.0 Air Conditioning and Mechanical Ventilation System | 1.1.7 The Perfomance of The Complete Ventilation, Pressurization, Exhaust and Smoke Spill System | 1.1.7 | The Perfomance of The Complete Ventilation, Pressurization, Exhaust and Smoke Spill System | M/6M | bar: T17
1.0 Air Conditioning and Mechanical Ventilation System | 1.4.1 Evaporator (Cooling Unit) | 1.4.1 | Evaporator (Cooling Unit) | D/M/Y |  |  | D | D | D | D | D |  |  | D | D | D | D | D |  |  | D | D | D | D | D |  |  | D, M |  | D | D | D
1.0 Air Conditioning and Mechanical Ventilation System | 1.4.2 Condenser | 1.4.2 | Condenser | M/Y | bar: T24
1.0 Air Conditioning and Mechanical Ventilation System | 1.4.3 Electrical Switchboard / Control Panel | 1.4.3 | Electrical Switchboard / Control Panel | M | bar: T24
1.0 Air Conditioning and Mechanical Ventilation System | 1.5.1 Evaporator / Condensor | 1.5.1 | Evaporator / Condensor | M/Y | bar: T24
1.0 Air Conditioning and Mechanical Ventilation System | 1.5.2 Electrical Switchboard / Control Panel | 1.5.2 | Electrical Switchboard / Control Panel | M/Y | bar: T24
1.0 Air Conditioning and Mechanical Ventilation System | 1.6 Piping and Fittings (Expose and Accessable) | 1.6 | Piping and Fittings (Expose and Accessable) | M/6M | bar: T24
1.0 Air Conditioning and Mechanical Ventilation System | 1.7 Painting | 1.7 | Painting | Y
2.0 Fire Fighting System |  | 2.1 | General | D/6M/Y | bar: T03 to T07; T10 to T14; T17 to T21; T24; T26 to T28
2.0 Fire Fighting System | 2.2.1 Pump Room | 2.2.1 | Pump Room | W/M/6M | bar: T03; T06; T13 to T14; T20; T27
2.0 Fire Fighting System | 2.2.2 Tank | 2.2.2 | Tank | W/M/6M/Y | bar: T03; T06; T13 to T14; T20; T27
2.0 Fire Fighting System | 2.2.3 Pumps (General) | i. | General | M | bar: T14
2.0 Fire Fighting System | 2.2.3 Pumps (General) | ii. | Control Panel | M | bar: T14
2.0 Fire Fighting System | 2.2.4 Piping and Fittings | 2.2.4 | Piping and Fittings | M/6M | bar: T14
2.0 Fire Fighting System | 2.2.5 Landing, Valves, Hose Reel Drums, Cradles, Hoses, Nozzles, etc. | 2.2.5 | Landing, Valves, Hose Reel Drums, Cradles, Hoses, Nozzles, etc. | M | bar: T14
2.0 Fire Fighting System | 2.2.6 Sprinkler System | 2.2.6 | Sprinkler System | M | bar: T14
2.0 Fire Fighting System | 2.2.7 Breeching Inlet | 2.2.7 | Breeching Inlet | M | bar: T14
2.0 Fire Fighting System | 2.3 Fire Detection and Alarm System | 2.3 | Fire Detection and Alarm System | D/M/6M |  |  | D | D | D | D | D |  |  | D | D | D | D | D |  |  | D, M | D | D | D | D |  |  | D |  | D | D | D
2.0 Fire Fighting System | 2.4.1 Panel | 2.4.1 | Panel | M | bar: T17
2.0 Fire Fighting System | 2.4.2 Battery | 2.4.2 | Battery | M | bar: T17
2.0 Fire Fighting System | 2.4.3 Automatic Control | 2.4.3 | Automatic Control | M | bar: T17
2.0 Fire Fighting System | 2.4.4 Electrical | 2.4.4 | Electrical | M | bar: T17
2.0 Fire Fighting System | 2.4.5 Handsets | 2.4.5 | Handsets | M | bar: T17
2.0 Fire Fighting System | 2.4.6 General | 2.4.6 | General | M | bar: T17
2.0 Fire Fighting System | 2.5.1 Cylinder, Hoses, Canister, etc. | 2.5.1 | Cylinder, Hoses, Canister, etc. | M | bar: T17
2.0 Fire Fighting System | 2.5.2 Pilot Cylinder | 2.5.2 | Pilot Cylinder | M | bar: T17
2.0 Fire Fighting System | 2.5.3 Panel | 2.5.3 | Panel | M | bar: T17
2.0 Fire Fighting System | 2.5.4 Devices | 2.5.4 | Devices | M/3M/6M | bar: T17
2.0 Fire Fighting System | 2.5.5 Aerohub | 2.5.5 | Aerohub | M/6M | bar: T17
2.0 Fire Fighting System | 2.6 Portable Fire Extinguisher | 2.6 | Portable Fire Extinguisher | M | bar: T17
2.0 Fire Fighting System | 2.7 BOMBA Link (SPKA) | 2.7 | BOMBA Link (SPKA) | M | bar: T17
2.0 Fire Fighting System | 2.8.1 General | 2.8.1 | General | M/Y | bar: T13
2.0 Fire Fighting System | 2.8.2 Pump Room | 2.8.2 | Pump Room | M | bar: T13
2.0 Fire Fighting System | 2.8.3 Tank | 2.8.3 | Tank | M/3M/6M/Y | bar: T13
2.0 Fire Fighting System | 2.8.4 Piping and Fitting | 2.8.4 | Piping and Fitting | M | bar: T13
2.0 Fire Fighting System | 2.8.5 Pump & Motor | 2.8.5 | Pump & Motor | M | bar: T13
2.0 Fire Fighting System | 2.9 Painting | 2.9 | Painting | 6M
3.0 LIFT |  | 3.1 | Motor Room | M | bar: T10
3.0 LIFT | 3.2 Hoist Way | 3.2 | Hoist Way | M | bar: T10
3.0 LIFT | 3.3 Lift Car | 3.3 | Lift Car | M /5Y | bar: T10
3.0 LIFT | 3.4 Entrance | 3.4 | Entrance | M | bar: T10
3.0 LIFT | 3.5 Lift Pit | 3.5 | Lift Pit | M | bar: T10
3.0 LIFT | 3.6 Automatic Rescue Device (ARD) | 3.6 | Automatic Rescue Device (ARD) | M | bar: T10
3.0 LIFT | 3.7 Building Control Room | 3.7 | Building Control Room | M | bar: T10
3.0 LIFT | 3.8 VIP Lift Access System | 3.8 | VIP Lift Access System | M | bar: T10
4.0 GONDOLA |  | 4.1 | Maintenance | M | bar: T10
5.0 Cold Water Supply and Booster Pump-Pump Room |  | 5.1 | Pump room | W/M/6M | bar: T03; T05; T12; T17; T19; T26
5.0 Cold Water Supply and Booster Pump-Pump Room | 5.2 Tanks (Suction & Storage) | 5.2 | Tanks (Suction & Storage) | M/6M | bar: T17
5.0 Cold Water Supply and Booster Pump-Pump Room | 5.3 Pumps | i. | General | M | bar: T17
5.0 Cold Water Supply and Booster Pump-Pump Room | 5.3 Pumps | ii. | Control Panel | M | bar: T17
5.0 Cold Water Supply and Booster Pump-Pump Room | 5.4 Piping & Fitting | 5.4 | Piping & Fitting | M/6M | bar: T17
5.0 Cold Water Supply and Booster Pump-Pump Room | 5.5 Pressure Vessel | 5.5 | Pressure Vessel | M | bar: T17
5.0 Cold Water Supply and Booster Pump-Pump Room | 5.6 Submersible Pumps | 5.6 | Submersible Pumps | W/M | bar: T03; T05; T12; T17; T19; T26
5.0 Cold Water Supply and Booster Pump-Pump Room | 5.7 Painting | 5.7 | Painting | 6M
6.0 Inspection of Mechanical Services Above Ceiling |  | 6 | Inspection of Mechanical Services Above Ceiling | 6M
7.0 Kitchen Equipment |  | 7 | Kitchen Equipment | 3M
7.0 Kitchen Equipment | 7.1 Open Burner Range | 7.1 | Open Burner Range | M/3M | bar: T10
7.0 Kitchen Equipment | 7.2 Hobs | 7.2 | Hobs | M | bar: T10
7.0 Kitchen Equipment | 7.3 Kitchen Hood | 7.3 | Kitchen Hood | W/M | bar: T03; T05; T10; T12; T19; T26
7.0 Kitchen Equipment | 7.4 Kitchen Exhaust Fan | 7.4 | Kitchen Exhaust Fan | M/6M/Y | bar: T10
8.0 Irrigation System and Landscape |  | 8.1 | Water pump | M/3M/Y | bar: T14
8.0 Irrigation System and Landscape | 8.2 Electrical Motor | 8.2 | Electrical Motor | M/3M/6M | bar: T14
8.0 Irrigation System and Landscape | 8.3 Electrical Switchboard / Control Panel | 8.3 | Electrical Switchboard / Control Panel | M/6M | bar: T14
8.0 Irrigation System and Landscape | 8.4 Piping | 8.4 | Piping | M | bar: T14
8.0 Irrigation System and Landscape | 8.5 Filter | 8.5 | Filter | M | bar: T14
8.0 Irrigation System and Landscape | 8.6 Skimmer | 8.6 | Skimmer | M | bar: T14
9.0 Other Mechanical Equipment System |  | i. | Operation | M | bar: T10
9.0 Other Mechanical Equipment System |  | ii. | Maintenance | M | bar: T10
9.0 Other Mechanical Equipment System | 9.1 Roller Shutter / Fire Roller Shutter | i. | General | M | bar: T10
9.0 Other Mechanical Equipment System | 9.1 Roller Shutter / Fire Roller Shutter | ii. | Electric Motors | M | bar: T10
9.0 Other Mechanical Equipment System | 9.1 Roller Shutter / Fire Roller Shutter | iii. | Electrical Switchboard / Control Panel | M | bar: T10
9.0 Other Mechanical Equipment System | 9.2 Hand Dryer | 9.2 | Hand Dryer | W/M | T03: W; T10: M, W; T17: W; T24: W
9.0 Other Mechanical Equipment System | 9.3 Grey Water Harvesting System | i. | General | W/M | T03: W; T10: M, W; T17: W; T24: W
9.0 Other Mechanical Equipment System | 9.4 Rain Water Harvesting System | i. | General | W/M | T03: W; T10: M, W; T17: W; T24: W
9.0 Other Mechanical Equipment System | 9.4 Rain Water Harvesting System | ii. | Control Panel | M | bar: T10

## September 2026
Sistem | Sub-Sistem | Item | Deskripsi | Kekerapan | T01 | T02 | T03 | T04 | T05 | T06 | T07 | T08 | T09 | T10 | T11 | T12 | T13 | T14 | T15 | T16 | T17 | T18 | T19 | T20 | T21 | T22 | T23 | T24 | T25 | T26 | T27 | T28 | T29 | T30
1.0 Air Conditioning and Mechanical Ventilation System | 1.1.1 Plant Room | i. | General | W/M/6M | bar: T04; T11; T18; T23; T25
1.0 Air Conditioning and Mechanical Ventilation System | 1.1.1 Plant Room | ii. | Chillers (Water Cooled) | D/M/6M/Y | D | D | D | D |  |  | D | D | D | D | D |  |  | D | D |  | D | D |  |  | D | D | D, M | D | D |  |  | D | D | D
1.0 Air Conditioning and Mechanical Ventilation System | 1.1.1 Plant Room | iii. | Chillers (Air Cooled Chiller System) | D/M/6M/Y | D | D | D | D |  |  | D | D | D | D | D |  |  | D | D |  | D | D |  |  | D | D | D, M | D | D |  |  | D | D | D
1.0 Air Conditioning and Mechanical Ventilation System | 1.1.1 Plant Room | iv. | Pumps | M | T23: D, M
1.0 Air Conditioning and Mechanical Ventilation System | 1.1.1 Plant Room | v. | Electric Motors | M/3M | bar: T23
1.0 Air Conditioning and Mechanical Ventilation System | 1.1.1 Plant Room | vi. | Electrical Switchboard/ Control Panel | M | bar: T28
1.0 Air Conditioning and Mechanical Ventilation System | 1.1.2 Heat Exchanger Plant Room | 1.1.2 | Heat Exchanger Plant Room | M/3M | bar: T28
1.0 Air Conditioning and Mechanical Ventilation System | 1.1.3 Cooling Towers | 1.1.3 | Cooling Towers | D/M | D | D | D | D |  |  | D | D | D | D | D |  |  | D | D |  | D | D |  |  | D | D, M | D | D | D |  |  | D | D | D
1.0 Air Conditioning and Mechanical Ventilation System | 1.1.4 Chilled Water Storage & Expansion Tank | 1.1.4 | Chilled Water Storage & Expansion Tank | W/M/Y | bar: T04; T11; T17 to T18; T25
1.0 Air Conditioning and Mechanical Ventilation System | 1.1.5 Air Handling Units and Fan-Coils | 1.1.5 | Air Handling Units and Fan-Coils | M/3M/6M/Y | bar: T17
1.0 Air Conditioning and Mechanical Ventilation System | 1.1.6 Ducting, Grilles and Dampers | 1.1.6 | Ducting, Grilles and Dampers | M/6M | bar: T17
1.0 Air Conditioning and Mechanical Ventilation System | 1.1.7 The Perfomance of The Complete Ventilation, Pressurization, Exhaust and Smoke Spill System | 1.1.7 | The Perfomance of The Complete Ventilation, Pressurization, Exhaust and Smoke Spill System | M/6M | bar: T17
1.0 Air Conditioning and Mechanical Ventilation System | 1.4.1 Evaporator (Cooling Unit) | 1.4.1 | Evaporator (Cooling Unit) | D/M/Y | D | D | D | D |  |  | D | D | D | D | D |  |  | D | D |  | D | D |  |  | D | D, M | D | D | D |  |  | D | D | D
1.0 Air Conditioning and Mechanical Ventilation System | 1.4.2 Condenser | 1.4.2 | Condenser | M/Y | bar: T22
1.0 Air Conditioning and Mechanical Ventilation System | 1.4.3 Electrical Switchboard / Control Panel | 1.4.3 | Electrical Switchboard / Control Panel | M | bar: T22
1.0 Air Conditioning and Mechanical Ventilation System | 1.5.1 Evaporator / Condensor | 1.5.1 | Evaporator / Condensor | M/Y | bar: T24
1.0 Air Conditioning and Mechanical Ventilation System | 1.5.2 Electrical Switchboard / Control Panel | 1.5.2 | Electrical Switchboard / Control Panel | M/Y | bar: T24
1.0 Air Conditioning and Mechanical Ventilation System | 1.6 Piping and Fittings (Expose and Accessable) | 1.6 | Piping and Fittings (Expose and Accessable) | M/6M | bar: T24
1.0 Air Conditioning and Mechanical Ventilation System | 1.7 Painting | 1.7 | Painting | Y
2.0 Fire Fighting System |  | 2.1 | General | D/6M/Y | bar: T01 to T04; T07 to T11; T14 to T15; T17 to T18; T21 to T25; T28 to T30
2.0 Fire Fighting System | 2.2.1 Pump Room | 2.2.1 | Pump Room | W/M/6M | bar: T03; T10; T14; T17; T24
2.0 Fire Fighting System | 2.2.2 Tank | 2.2.2 | Tank | W/M/6M/Y | bar: T03; T10; T14; T17; T24
2.0 Fire Fighting System | 2.2.3 Pumps (General) | i. | General | M | bar: T14
2.0 Fire Fighting System | 2.2.3 Pumps (General) | ii. | Control Panel | M | bar: T14
2.0 Fire Fighting System | 2.2.4 Piping and Fittings | 2.2.4 | Piping and Fittings | M/6M | bar: T14
2.0 Fire Fighting System | 2.2.5 Landing, Valves, Hose Reel Drums, Cradles, Hoses, Nozzles, etc. | 2.2.5 | Landing, Valves, Hose Reel Drums, Cradles, Hoses, Nozzles, etc. | M | bar: T14
2.0 Fire Fighting System | 2.2.6 Sprinkler System | 2.2.6 | Sprinkler System | M | bar: T14
2.0 Fire Fighting System | 2.2.7 Breeching Inlet | 2.2.7 | Breeching Inlet | M | bar: T14
2.0 Fire Fighting System | 2.3 Fire Detection and Alarm System | 2.3 | Fire Detection and Alarm System | D/M/6M | D | D | D | D |  |  | D | D | D | D | D |  |  | D | D, M |  | D | D |  |  | D | D | D | D | D |  |  | D | D | D
2.0 Fire Fighting System | 2.4.1 Panel | 2.4.1 | Panel | M | bar: T15
2.0 Fire Fighting System | 2.4.2 Battery | 2.4.2 | Battery | M | bar: T15
2.0 Fire Fighting System | 2.4.3 Automatic Control | 2.4.3 | Automatic Control | M | bar: T15
2.0 Fire Fighting System | 2.4.4 Electrical | 2.4.4 | Electrical | M | bar: T15
2.0 Fire Fighting System | 2.4.5 Handsets | 2.4.5 | Handsets | M | bar: T15
2.0 Fire Fighting System | 2.4.6 General | 2.4.6 | General | M | bar: T15
2.0 Fire Fighting System | 2.5.1 Cylinder, Hoses, Canister, etc. | 2.5.1 | Cylinder, Hoses, Canister, etc. | M | bar: T15
2.0 Fire Fighting System | 2.5.2 Pilot Cylinder | 2.5.2 | Pilot Cylinder | M | bar: T15
2.0 Fire Fighting System | 2.5.3 Panel | 2.5.3 | Panel | M | bar: T15
2.0 Fire Fighting System | 2.5.4 Devices | 2.5.4 | Devices | M/3M/6M | bar: T15
2.0 Fire Fighting System | 2.5.5 Aerohub | 2.5.5 | Aerohub | M/6M | bar: T15
2.0 Fire Fighting System | 2.6 Portable Fire Extinguisher | 2.6 | Portable Fire Extinguisher | M | bar: T15
2.0 Fire Fighting System | 2.7 BOMBA Link (SPKA) | 2.7 | BOMBA Link (SPKA) | M | bar: T15
2.0 Fire Fighting System | 2.8.1 General | 2.8.1 | General | M/Y | bar: T14
2.0 Fire Fighting System | 2.8.2 Pump Room | 2.8.2 | Pump Room | M | bar: T14
2.0 Fire Fighting System | 2.8.3 Tank | 2.8.3 | Tank | M/3M/6M/Y | bar: T14
2.0 Fire Fighting System | 2.8.4 Piping and Fitting | 2.8.4 | Piping and Fitting | M | bar: T14
2.0 Fire Fighting System | 2.8.5 Pump & Motor | 2.8.5 | Pump & Motor | M | bar: T14
2.0 Fire Fighting System | 2.9 Painting | 2.9 | Painting | 6M
3.0 LIFT |  | 3.1 | Motor Room | M | bar: T09
3.0 LIFT | 3.2 Hoist Way | 3.2 | Hoist Way | M | bar: T09
3.0 LIFT | 3.3 Lift Car | 3.3 | Lift Car | M /5Y | bar: T09
3.0 LIFT | 3.4 Entrance | 3.4 | Entrance | M | bar: T09
3.0 LIFT | 3.5 Lift Pit | 3.5 | Lift Pit | M | bar: T09
3.0 LIFT | 3.6 Automatic Rescue Device (ARD) | 3.6 | Automatic Rescue Device (ARD) | M | bar: T09
3.0 LIFT | 3.7 Building Control Room | 3.7 | Building Control Room | M | bar: T09
3.0 LIFT | 3.8 VIP Lift Access System | 3.8 | VIP Lift Access System | M | bar: T09
4.0 GONDOLA |  | 4.1 | Maintenance | M | bar: T08
5.0 Cold Water Supply and Booster Pump-Pump Room |  | 5.1 | Pump room | W/M/6M | T02: W; T09: W; T17: M, W; T23: W; T30: W
5.0 Cold Water Supply and Booster Pump-Pump Room | 5.2 Tanks (Suction & Storage) | 5.2 | Tanks (Suction & Storage) | M/6M | bar: T17
5.0 Cold Water Supply and Booster Pump-Pump Room | 5.3 Pumps | i. | General | M | bar: T17
5.0 Cold Water Supply and Booster Pump-Pump Room | 5.3 Pumps | ii. | Control Panel | M | bar: T17
5.0 Cold Water Supply and Booster Pump-Pump Room | 5.4 Piping & Fitting | 5.4 | Piping & Fitting | M/6M | bar: T17
5.0 Cold Water Supply and Booster Pump-Pump Room | 5.5 Pressure Vessel | 5.5 | Pressure Vessel | M | bar: T17
5.0 Cold Water Supply and Booster Pump-Pump Room | 5.6 Submersible Pumps | 5.6 | Submersible Pumps | W/M | T02: W; T09: W; T17: M, W; T23: W; T30: W
5.0 Cold Water Supply and Booster Pump-Pump Room | 5.7 Painting | 5.7 | Painting | 6M
6.0 Inspection of Mechanical Services Above Ceiling |  | 6 | Inspection of Mechanical Services Above Ceiling | 6M
7.0 Kitchen Equipment |  | 7 | Kitchen Equipment | 3M
7.0 Kitchen Equipment | 7.1 Open Burner Range | 7.1 | Open Burner Range | M/3M | bar: T10
7.0 Kitchen Equipment | 7.2 Hobs | 7.2 | Hobs | M | bar: T10
7.0 Kitchen Equipment | 7.3 Kitchen Hood | 7.3 | Kitchen Hood | W/M | bar: T02; T09 to T10; T17; T23; T30
7.0 Kitchen Equipment | 7.4 Kitchen Exhaust Fan | 7.4 | Kitchen Exhaust Fan | M/6M/Y | bar: T10
8.0 Irrigation System and Landscape |  | 8.1 | Water pump | M/3M/Y | bar: T14
8.0 Irrigation System and Landscape | 8.2 Electrical Motor | 8.2 | Electrical Motor | M/3M/6M | bar: T14
8.0 Irrigation System and Landscape | 8.3 Electrical Switchboard / Control Panel | 8.3 | Electrical Switchboard / Control Panel | M/6M | bar: T14
8.0 Irrigation System and Landscape | 8.4 Piping | 8.4 | Piping | M | bar: T14
8.0 Irrigation System and Landscape | 8.5 Filter | 8.5 | Filter | M | bar: T14
8.0 Irrigation System and Landscape | 8.6 Skimmer | 8.6 | Skimmer | M | bar: T14
9.0 Other Mechanical Equipment System |  | i. | Operation | M | bar: T09
9.0 Other Mechanical Equipment System |  | ii. | Maintenance | M | bar: T09
9.0 Other Mechanical Equipment System | 9.1 Roller Shutter / Fire Roller Shutter | i. | General | M | bar: T09
9.0 Other Mechanical Equipment System | 9.1 Roller Shutter / Fire Roller Shutter | ii. | Electric Motors | M | bar: T09
9.0 Other Mechanical Equipment System | 9.1 Roller Shutter / Fire Roller Shutter | iii. | Electrical Switchboard / Control Panel | M | bar: T09
9.0 Other Mechanical Equipment System | 9.2 Hand Dryer | 9.2 | Hand Dryer | W/M | bar: T01; T07; T09; T14; T21; T28
9.0 Other Mechanical Equipment System | 9.3 Grey Water Harvesting System | i. | General | W/M | bar: T01; T07; T09; T14; T21; T28
9.0 Other Mechanical Equipment System | 9.4 Rain Water Harvesting System | i. | General | W/M | bar: T01; T07; T09; T14; T21; T28
9.0 Other Mechanical Equipment System | 9.4 Rain Water Harvesting System | ii. | Control Panel | M | bar: T09

## Oktober 2026
Sistem | Sub-Sistem | Item | Deskripsi | Kekerapan | T01 | T02 | T03 | T04 | T05 | T06 | T07 | T08 | T09 | T10 | T11 | T12 | T13 | T14 | T15 | T16 | T17 | T18 | T19 | T20 | T21 | T22 | T23 | T24 | T25 | T26 | T27 | T28 | T29 | T30 | T31
1.0 Air Conditioning and Mechanical Ventilation System | 1.1.1 Plant Room | i. | General | W/M/6M | T02: W; T09: W; T16: W; T23: M, W; T30: W
1.0 Air Conditioning and Mechanical Ventilation System | 1.1.1 Plant Room | ii. | Chillers (Water Cooled) | D/M/6M/Y | D | D |  |  | D | D | D | D | D |  |  | D | D | D | D | D |  |  | D | D | D | D | D, M |  |  | D | D | D | D | D
1.0 Air Conditioning and Mechanical Ventilation System | 1.1.1 Plant Room | iii. | Chillers (Air Cooled Chiller System) | D/M/6M/Y | D | D |  |  | D | D | D | D | D |  |  | D | D | D | D | D |  |  | D | D | D | D | D, M |  |  | D | D | D | D | D
1.0 Air Conditioning and Mechanical Ventilation System | 1.1.1 Plant Room | iv. | Pumps | M | T23: D, M
1.0 Air Conditioning and Mechanical Ventilation System | 1.1.1 Plant Room | v. | Electric Motors | M/3M | bar: T23; T26
1.0 Air Conditioning and Mechanical Ventilation System | 1.1.1 Plant Room | vi. | Electrical Switchboard/ Control Panel | M | bar: T28
1.0 Air Conditioning and Mechanical Ventilation System | 1.1.2 Heat Exchanger Plant Room | 1.1.2 | Heat Exchanger Plant Room | M/3M | bar: T28 to T29
1.0 Air Conditioning and Mechanical Ventilation System | 1.1.3 Cooling Towers | 1.1.3 | Cooling Towers | D/M | D | D |  |  | D | D | D | D | D |  |  | D | D | D | D | D |  |  | D | D | D | D, M | D |  |  | D | D | D | D | D
1.0 Air Conditioning and Mechanical Ventilation System | 1.1.4 Chilled Water Storage & Expansion Tank | 1.1.4 | Chilled Water Storage & Expansion Tank | W/M/Y | T02: W; T09: W; T16: M, W; T23: W; T30: W
1.0 Air Conditioning and Mechanical Ventilation System | 1.1.5 Air Handling Units and Fan-Coils | 1.1.5 | Air Handling Units and Fan-Coils | M/3M/6M/Y | bar: T16; T26
1.0 Air Conditioning and Mechanical Ventilation System | 1.1.6 Ducting, Grilles and Dampers | 1.1.6 | Ducting, Grilles and Dampers | M/6M | bar: T16
1.0 Air Conditioning and Mechanical Ventilation System | 1.1.7 The Perfomance of The Complete Ventilation, Pressurization, Exhaust and Smoke Spill System | 1.1.7 | The Perfomance of The Complete Ventilation, Pressurization, Exhaust and Smoke Spill System | M/6M | bar: T16
1.0 Air Conditioning and Mechanical Ventilation System | 1.4.1 Evaporator (Cooling Unit) | 1.4.1 | Evaporator (Cooling Unit) | D/M/Y | D | D |  |  | D | D | D | D | D |  |  | D | D | D | D | D |  |  | D | D | D | D, M | D |  |  | D | D | D | D | D
1.0 Air Conditioning and Mechanical Ventilation System | 1.4.2 Condenser | 1.4.2 | Condenser | M/Y | bar: T22
1.0 Air Conditioning and Mechanical Ventilation System | 1.4.3 Electrical Switchboard / Control Panel | 1.4.3 | Electrical Switchboard / Control Panel | M | bar: T22
1.0 Air Conditioning and Mechanical Ventilation System | 1.5.1 Evaporator / Condensor | 1.5.1 | Evaporator / Condensor | M/Y | bar: T26
1.0 Air Conditioning and Mechanical Ventilation System | 1.5.2 Electrical Switchboard / Control Panel | 1.5.2 | Electrical Switchboard / Control Panel | M/Y | bar: T26
1.0 Air Conditioning and Mechanical Ventilation System | 1.6 Piping and Fittings (Expose and Accessable) | 1.6 | Piping and Fittings (Expose and Accessable) | M/6M | bar: T26
1.0 Air Conditioning and Mechanical Ventilation System | 1.7 Painting | 1.7 | Painting | Y
2.0 Fire Fighting System |  | 2.1 | General | D/6M/Y | bar: T01 to T02; T05 to T09; T12 to T16; T19 to T23; T26 to T30
2.0 Fire Fighting System | 2.2.1 Pump Room | 2.2.1 | Pump Room | W/M/6M | bar: T01; T08; T14 to T15; T22; T29
2.0 Fire Fighting System | 2.2.2 Tank | 2.2.2 | Tank | W/M/6M/Y | bar: T01; T08; T14 to T15; T22; T29
2.0 Fire Fighting System | 2.2.3 Pumps (General) | i. | General | M | bar: T14
2.0 Fire Fighting System | 2.2.3 Pumps (General) | ii. | Control Panel | M | bar: T14
2.0 Fire Fighting System | 2.2.4 Piping and Fittings | 2.2.4 | Piping and Fittings | M/6M | bar: T14
2.0 Fire Fighting System | 2.2.5 Landing, Valves, Hose Reel Drums, Cradles, Hoses, Nozzles, etc. | 2.2.5 | Landing, Valves, Hose Reel Drums, Cradles, Hoses, Nozzles, etc. | M | bar: T14
2.0 Fire Fighting System | 2.2.6 Sprinkler System | 2.2.6 | Sprinkler System | M | bar: T14
2.0 Fire Fighting System | 2.2.7 Breeching Inlet | 2.2.7 | Breeching Inlet | M | bar: T14
2.0 Fire Fighting System | 2.3 Fire Detection and Alarm System | 2.3 | Fire Detection and Alarm System | D/M/6M | D | D |  |  | D | D | D | D | D |  |  | D | D | D | D, M | D |  |  | D | D | D | D | D |  |  | D | D | D | D | D
2.0 Fire Fighting System | 2.4.1 Panel | 2.4.1 | Panel | M | bar: T15
2.0 Fire Fighting System | 2.4.2 Battery | 2.4.2 | Battery | M | bar: T15
2.0 Fire Fighting System | 2.4.3 Automatic Control | 2.4.3 | Automatic Control | M | bar: T15
2.0 Fire Fighting System | 2.4.4 Electrical | 2.4.4 | Electrical | M | bar: T15
2.0 Fire Fighting System | 2.4.5 Handsets | 2.4.5 | Handsets | M | bar: T15
2.0 Fire Fighting System | 2.4.6 General | 2.4.6 | General | M | bar: T15
2.0 Fire Fighting System | 2.5.1 Cylinder, Hoses, Canister, etc. | 2.5.1 | Cylinder, Hoses, Canister, etc. | M | bar: T15
2.0 Fire Fighting System | 2.5.2 Pilot Cylinder | 2.5.2 | Pilot Cylinder | M | bar: T15
2.0 Fire Fighting System | 2.5.3 Panel | 2.5.3 | Panel | M | bar: T15
2.0 Fire Fighting System | 2.5.4 Devices | 2.5.4 | Devices | M/3M/6M | bar: T15; T22
2.0 Fire Fighting System | 2.5.5 Aerohub | 2.5.5 | Aerohub | M/6M | bar: T15
2.0 Fire Fighting System | 2.6 Portable Fire Extinguisher | 2.6 | Portable Fire Extinguisher | M | bar: T15
2.0 Fire Fighting System | 2.7 BOMBA Link (SPKA) | 2.7 | BOMBA Link (SPKA) | M | bar: T15
2.0 Fire Fighting System | 2.8.1 General | 2.8.1 | General | M/Y | bar: T13
2.0 Fire Fighting System | 2.8.2 Pump Room | 2.8.2 | Pump Room | M | bar: T13
2.0 Fire Fighting System | 2.8.3 Tank | 2.8.3 | Tank | M/3M/6M/Y | bar: T13; T19
2.0 Fire Fighting System | 2.8.4 Piping and Fitting | 2.8.4 | Piping and Fitting | M | bar: T13
2.0 Fire Fighting System | 2.8.5 Pump & Motor | 2.8.5 | Pump & Motor | M | bar: T13
2.0 Fire Fighting System | 2.9 Painting | 2.9 | Painting | 6M
3.0 LIFT |  | 3.1 | Motor Room | M | bar: T09
3.0 LIFT | 3.2 Hoist Way | 3.2 | Hoist Way | M | bar: T09
3.0 LIFT | 3.3 Lift Car | 3.3 | Lift Car | M /5Y | bar: T09
3.0 LIFT | 3.4 Entrance | 3.4 | Entrance | M | bar: T09
3.0 LIFT | 3.5 Lift Pit | 3.5 | Lift Pit | M | bar: T09
3.0 LIFT | 3.6 Automatic Rescue Device (ARD) | 3.6 | Automatic Rescue Device (ARD) | M | bar: T09
3.0 LIFT | 3.7 Building Control Room | 3.7 | Building Control Room | M | bar: T09
3.0 LIFT | 3.8 VIP Lift Access System | 3.8 | VIP Lift Access System | M | bar: T09
4.0 GONDOLA |  | 4.1 | Maintenance | M | bar: T08
5.0 Cold Water Supply and Booster Pump-Pump Room |  | 5.1 | Pump room | W/M/6M | bar: T01; T07; T14; T19; T21; T28
5.0 Cold Water Supply and Booster Pump-Pump Room | 5.2 Tanks (Suction & Storage) | 5.2 | Tanks (Suction & Storage) | M/6M | bar: T19
5.0 Cold Water Supply and Booster Pump-Pump Room | 5.3 Pumps | i. | General | M | bar: T19
5.0 Cold Water Supply and Booster Pump-Pump Room | 5.3 Pumps | ii. | Control Panel | M | bar: T19
5.0 Cold Water Supply and Booster Pump-Pump Room | 5.4 Piping & Fitting | 5.4 | Piping & Fitting | M/6M | bar: T19
5.0 Cold Water Supply and Booster Pump-Pump Room | 5.5 Pressure Vessel | 5.5 | Pressure Vessel | M | bar: T19
5.0 Cold Water Supply and Booster Pump-Pump Room | 5.6 Submersible Pumps | 5.6 | Submersible Pumps | W/M | bar: T01; T07; T14; T19; T21; T28
5.0 Cold Water Supply and Booster Pump-Pump Room | 5.7 Painting | 5.7 | Painting | 6M
6.0 Inspection of Mechanical Services Above Ceiling |  | 6 | Inspection of Mechanical Services Above Ceiling | 6M
7.0 Kitchen Equipment |  | 7 | Kitchen Equipment | 3M | bar: T21
7.0 Kitchen Equipment | 7.1 Open Burner Range | 7.1 | Open Burner Range | M/3M | bar: T12; T21
7.0 Kitchen Equipment | 7.2 Hobs | 7.2 | Hobs | M | bar: T12
7.0 Kitchen Equipment | 7.3 Kitchen Hood | 7.3 | Kitchen Hood | W/M | bar: T01; T07; T12; T14; T21; T28
7.0 Kitchen Equipment | 7.4 Kitchen Exhaust Fan | 7.4 | Kitchen Exhaust Fan | M/6M/Y | bar: T12
8.0 Irrigation System and Landscape |  | 8.1 | Water pump | M/3M/Y | bar: T14; T19
8.0 Irrigation System and Landscape | 8.2 Electrical Motor | 8.2 | Electrical Motor | M/3M/6M | bar: T14; T19
8.0 Irrigation System and Landscape | 8.3 Electrical Switchboard / Control Panel | 8.3 | Electrical Switchboard / Control Panel | M/6M | bar: T14
8.0 Irrigation System and Landscape | 8.4 Piping | 8.4 | Piping | M | bar: T14
8.0 Irrigation System and Landscape | 8.5 Filter | 8.5 | Filter | M | bar: T14
8.0 Irrigation System and Landscape | 8.6 Skimmer | 8.6 | Skimmer | M | bar: T14
9.0 Other Mechanical Equipment System |  | i. | Operation | M | bar: T09
9.0 Other Mechanical Equipment System |  | ii. | Maintenance | M | bar: T09
9.0 Other Mechanical Equipment System | 9.1 Roller Shutter / Fire Roller Shutter | i. | General | M | bar: T09
9.0 Other Mechanical Equipment System | 9.1 Roller Shutter / Fire Roller Shutter | ii. | Electric Motors | M | bar: T09
9.0 Other Mechanical Equipment System | 9.1 Roller Shutter / Fire Roller Shutter | iii. | Electrical Switchboard / Control Panel | M | bar: T09
9.0 Other Mechanical Equipment System | 9.2 Hand Dryer | 9.2 | Hand Dryer | W/M | bar: T01; T05; T09; T12; T19; T26
9.0 Other Mechanical Equipment System | 9.3 Grey Water Harvesting System | i. | General | W/M | bar: T01; T05; T09; T12; T19; T26
9.0 Other Mechanical Equipment System | 9.4 Rain Water Harvesting System | i. | General | W/M | bar: T01; T05; T09; T12; T19; T26
9.0 Other Mechanical Equipment System | 9.4 Rain Water Harvesting System | ii. | Control Panel | M | bar: T09

## November 2026
Sistem | Sub-Sistem | Item | Deskripsi | Kekerapan | T01 | T02 | T03 | T04 | T05 | T06 | T07 | T08 | T09 | T10 | T11 | T12 | T13 | T14 | T15 | T16 | T17 | T18 | T19 | T20 | T21 | T22 | T23 | T24 | T25 | T26 | T27 | T28 | T29 | T30
1.0 Air Conditioning and Mechanical Ventilation System | 1.1.1 Plant Room | i. | General | W/M/6M | bar: T02; T06; T13; T20; T23; T27
1.0 Air Conditioning and Mechanical Ventilation System | 1.1.1 Plant Room | ii. | Chillers (Water Cooled) | D/M/6M/Y |  | D | D | D | D | D |  |  |  | D | D | D | D |  |  | D | D | D | D | D |  |  | D, M | D | D | D | D, Y |  |  | D
1.0 Air Conditioning and Mechanical Ventilation System | 1.1.1 Plant Room | iii. | Chillers (Air Cooled Chiller System) | D/M/6M/Y |  | D | D | D | D | D |  |  |  | D | D | D | D |  |  | D | D | D | D | D |  |  | D, M | D | D | D | D, Y |  |  | D
1.0 Air Conditioning and Mechanical Ventilation System | 1.1.1 Plant Room | iv. | Pumps | M | T23: D, M
1.0 Air Conditioning and Mechanical Ventilation System | 1.1.1 Plant Room | v. | Electric Motors | M/3M | bar: T23
1.0 Air Conditioning and Mechanical Ventilation System | 1.1.1 Plant Room | vi. | Electrical Switchboard/ Control Panel | M | bar: T30
1.0 Air Conditioning and Mechanical Ventilation System | 1.1.2 Heat Exchanger Plant Room | 1.1.2 | Heat Exchanger Plant Room | M/3M | bar: T30
1.0 Air Conditioning and Mechanical Ventilation System | 1.1.3 Cooling Towers | 1.1.3 | Cooling Towers | D/M |  | D | D | D | D | D |  |  |  | D | D | D | D |  |  | D | D | D | D | D |  |  | D, M | D | D | D | D |  |  | D
1.0 Air Conditioning and Mechanical Ventilation System | 1.1.4 Chilled Water Storage & Expansion Tank | 1.1.4 | Chilled Water Storage & Expansion Tank | W/M/Y | T02: W; T06: W; T13: W; T16: M, Y; T20: W; T27: W
1.0 Air Conditioning and Mechanical Ventilation System | 1.1.5 Air Handling Units and Fan-Coils | 1.1.5 | Air Handling Units and Fan-Coils | M/3M/6M/Y | bar: T16; T27
1.0 Air Conditioning and Mechanical Ventilation System | 1.1.6 Ducting, Grilles and Dampers | 1.1.6 | Ducting, Grilles and Dampers | M/6M | bar: T16
1.0 Air Conditioning and Mechanical Ventilation System | 1.1.7 The Perfomance of The Complete Ventilation, Pressurization, Exhaust and Smoke Spill System | 1.1.7 | The Perfomance of The Complete Ventilation, Pressurization, Exhaust and Smoke Spill System | M/6M | bar: T16
1.0 Air Conditioning and Mechanical Ventilation System | 1.4.1 Evaporator (Cooling Unit) | 1.4.1 | Evaporator (Cooling Unit) | D/M/Y |  | D | D | D | D | D |  |  |  | D | D | D | D |  |  | D | D | D | D | D |  |  | D, M, Y | D | D | D | D |  |  | D
1.0 Air Conditioning and Mechanical Ventilation System | 1.4.2 Condenser | 1.4.2 | Condenser | M/Y | T23: M, Y
1.0 Air Conditioning and Mechanical Ventilation System | 1.4.3 Electrical Switchboard / Control Panel | 1.4.3 | Electrical Switchboard / Control Panel | M | bar: T23
1.0 Air Conditioning and Mechanical Ventilation System | 1.5.1 Evaporator / Condensor | 1.5.1 | Evaporator / Condensor | M/Y | T24: M, Y
1.0 Air Conditioning and Mechanical Ventilation System | 1.5.2 Electrical Switchboard / Control Panel | 1.5.2 | Electrical Switchboard / Control Panel | M/Y | T24: M, Y
1.0 Air Conditioning and Mechanical Ventilation System | 1.6 Piping and Fittings (Expose and Accessable) | 1.6 | Piping and Fittings (Expose and Accessable) | M/6M | bar: T24
1.0 Air Conditioning and Mechanical Ventilation System | 1.7 Painting | 1.7 | Painting | Y | bar: T23
2.0 Fire Fighting System |  | 2.1 | General | D/6M/Y |  | D | D | D | D | D |  |  |  | D | D | D | D |  |  | D | D | D | D | D |  |  | D, Y | D | D | D | D |  |  | D
2.0 Fire Fighting System | 2.2.1 Pump Room | 2.2.1 | Pump Room | W/M/6M | bar: T02; T05; T12; T16; T19; T26
2.0 Fire Fighting System | 2.2.2 Tank | 2.2.2 | Tank | W/M/6M/Y | T02: W; T05: W; T12: W; T16: M, Y; T19: W; T26: W
2.0 Fire Fighting System | 2.2.3 Pumps (General) | i. | General | M | bar: T16
2.0 Fire Fighting System | 2.2.3 Pumps (General) | ii. | Control Panel | M | bar: T16
2.0 Fire Fighting System | 2.2.4 Piping and Fittings | 2.2.4 | Piping and Fittings | M/6M | bar: T16
2.0 Fire Fighting System | 2.2.5 Landing, Valves, Hose Reel Drums, Cradles, Hoses, Nozzles, etc. | 2.2.5 | Landing, Valves, Hose Reel Drums, Cradles, Hoses, Nozzles, etc. | M | bar: T16
2.0 Fire Fighting System | 2.2.6 Sprinkler System | 2.2.6 | Sprinkler System | M | bar: T16
2.0 Fire Fighting System | 2.2.7 Breeching Inlet | 2.2.7 | Breeching Inlet | M | bar: T16
2.0 Fire Fighting System | 2.3 Fire Detection and Alarm System | 2.3 | Fire Detection and Alarm System | D/M/6M |  | D | D | D | D | D |  |  |  | D | D | D | D |  |  | D, M | D | D | D | D |  |  | D | D | D | D | D |  |  | D
2.0 Fire Fighting System | 2.4.1 Panel | 2.4.1 | Panel | M | bar: T16
2.0 Fire Fighting System | 2.4.2 Battery | 2.4.2 | Battery | M | bar: T16
2.0 Fire Fighting System | 2.4.3 Automatic Control | 2.4.3 | Automatic Control | M | bar: T16
2.0 Fire Fighting System | 2.4.4 Electrical | 2.4.4 | Electrical | M | bar: T16
2.0 Fire Fighting System | 2.4.5 Handsets | 2.4.5 | Handsets | M | bar: T16
2.0 Fire Fighting System | 2.4.6 General | 2.4.6 | General | M | bar: T16
2.0 Fire Fighting System | 2.5.1 Cylinder, Hoses, Canister, etc. | 2.5.1 | Cylinder, Hoses, Canister, etc. | M | bar: T16
2.0 Fire Fighting System | 2.5.2 Pilot Cylinder | 2.5.2 | Pilot Cylinder | M | bar: T16
2.0 Fire Fighting System | 2.5.3 Panel | 2.5.3 | Panel | M | bar: T16
2.0 Fire Fighting System | 2.5.4 Devices | 2.5.4 | Devices | M/3M/6M | bar: T16
2.0 Fire Fighting System | 2.5.5 Aerohub | 2.5.5 | Aerohub | M/6M | bar: T16
2.0 Fire Fighting System | 2.6 Portable Fire Extinguisher | 2.6 | Portable Fire Extinguisher | M | bar: T16
2.0 Fire Fighting System | 2.7 BOMBA Link (SPKA) | 2.7 | BOMBA Link (SPKA) | M | bar: T16
2.0 Fire Fighting System | 2.8.1 General | 2.8.1 | General | M/Y | T13: M, Y
2.0 Fire Fighting System | 2.8.2 Pump Room | 2.8.2 | Pump Room | M | bar: T13
2.0 Fire Fighting System | 2.8.3 Tank | 2.8.3 | Tank | M/3M/6M/Y | T13: M, Y
2.0 Fire Fighting System | 2.8.4 Piping and Fitting | 2.8.4 | Piping and Fitting | M | bar: T13
2.0 Fire Fighting System | 2.8.5 Pump & Motor | 2.8.5 | Pump & Motor | M | bar: T13
2.0 Fire Fighting System | 2.9 Painting | 2.9 | Painting | 6M
3.0 LIFT |  | 3.1 | Motor Room | M | bar: T10
3.0 LIFT | 3.2 Hoist Way | 3.2 | Hoist Way | M | bar: T10
3.0 LIFT | 3.3 Lift Car | 3.3 | Lift Car | M /5Y | bar: T10
3.0 LIFT | 3.4 Entrance | 3.4 | Entrance | M | bar: T10
3.0 LIFT | 3.5 Lift Pit | 3.5 | Lift Pit | M | bar: T10
3.0 LIFT | 3.6 Automatic Rescue Device (ARD) | 3.6 | Automatic Rescue Device (ARD) | M | bar: T10
3.0 LIFT | 3.7 Building Control Room | 3.7 | Building Control Room | M | bar: T10
3.0 LIFT | 3.8 VIP Lift Access System | 3.8 | VIP Lift Access System | M | bar: T10
4.0 GONDOLA |  | 4.1 | Maintenance | M | bar: T10
5.0 Cold Water Supply and Booster Pump-Pump Room |  | 5.1 | Pump room | W/M/6M | bar: T02; T04; T11; T17 to T18; T25
5.0 Cold Water Supply and Booster Pump-Pump Room | 5.2 Tanks (Suction & Storage) | 5.2 | Tanks (Suction & Storage) | M/6M | bar: T17
5.0 Cold Water Supply and Booster Pump-Pump Room | 5.3 Pumps | i. | General | M | bar: T17
5.0 Cold Water Supply and Booster Pump-Pump Room | 5.3 Pumps | ii. | Control Panel | M | bar: T17
5.0 Cold Water Supply and Booster Pump-Pump Room | 5.4 Piping & Fitting | 5.4 | Piping & Fitting | M/6M | bar: T17
5.0 Cold Water Supply and Booster Pump-Pump Room | 5.5 Pressure Vessel | 5.5 | Pressure Vessel | M | bar: T17
5.0 Cold Water Supply and Booster Pump-Pump Room | 5.6 Submersible Pumps | 5.6 | Submersible Pumps | W/M | bar: T02; T04; T11; T17 to T18; T25
5.0 Cold Water Supply and Booster Pump-Pump Room | 5.7 Painting | 5.7 | Painting | 6M
6.0 Inspection of Mechanical Services Above Ceiling |  | 6 | Inspection of Mechanical Services Above Ceiling | 6M
7.0 Kitchen Equipment |  | 7 | Kitchen Equipment | 3M
7.0 Kitchen Equipment | 7.1 Open Burner Range | 7.1 | Open Burner Range | M/3M | bar: T10
7.0 Kitchen Equipment | 7.2 Hobs | 7.2 | Hobs | M | bar: T10
7.0 Kitchen Equipment | 7.3 Kitchen Hood | 7.3 | Kitchen Hood | W/M | bar: T02; T04; T10 to T11; T18; T25
7.0 Kitchen Equipment | 7.4 Kitchen Exhaust Fan | 7.4 | Kitchen Exhaust Fan | M/6M/Y | T10: M, Y
8.0 Irrigation System and Landscape |  | 8.1 | Water pump | M/3M/Y | T16: M, Y
8.0 Irrigation System and Landscape | 8.2 Electrical Motor | 8.2 | Electrical Motor | M/3M/6M | bar: T16
8.0 Irrigation System and Landscape | 8.3 Electrical Switchboard / Control Panel | 8.3 | Electrical Switchboard / Control Panel | M/6M | bar: T16
8.0 Irrigation System and Landscape | 8.4 Piping | 8.4 | Piping | M | bar: T16
8.0 Irrigation System and Landscape | 8.5 Filter | 8.5 | Filter | M | bar: T16
8.0 Irrigation System and Landscape | 8.6 Skimmer | 8.6 | Skimmer | M | bar: T16
9.0 Other Mechanical Equipment System |  | i. | Operation | M | bar: T10
9.0 Other Mechanical Equipment System |  | ii. | Maintenance | M | bar: T10
9.0 Other Mechanical Equipment System | 9.1 Roller Shutter / Fire Roller Shutter | i. | General | M | bar: T10
9.0 Other Mechanical Equipment System | 9.1 Roller Shutter / Fire Roller Shutter | ii. | Electric Motors | M | bar: T10
9.0 Other Mechanical Equipment System | 9.1 Roller Shutter / Fire Roller Shutter | iii. | Electrical Switchboard / Control Panel | M | bar: T10
9.0 Other Mechanical Equipment System | 9.2 Hand Dryer | 9.2 | Hand Dryer | W/M | T02: W; T10: M, W; T16: W; T23: W
9.0 Other Mechanical Equipment System | 9.3 Grey Water Harvesting System | i. | General | W/M | T02: W; T10: M, W; T16: W; T23: W
9.0 Other Mechanical Equipment System | 9.4 Rain Water Harvesting System | i. | General | W/M | T02: W; T10: M, W; T16: W; T23: W
9.0 Other Mechanical Equipment System | 9.4 Rain Water Harvesting System | ii. | Control Panel | M | bar: T10

## Disember 2026
Sistem | Sub-Sistem | Item | Deskripsi | Kekerapan | T01 | T02 | T03 | T04 | T05 | T06 | T07 | T08 | T09 | T10 | T11 | T12 | T13 | T14 | T15 | T16 | T17 | T18 | T19 | T20 | T21 | T22 | T23 | T24 | T25 | T26 | T27 | T28 | T29 | T30 | T31
1.0 Air Conditioning and Mechanical Ventilation System | 1.1.1 Plant Room | i. | General | W/M/6M | bar: T04; T11; T18; T23; T28
1.0 Air Conditioning and Mechanical Ventilation System | 1.1.1 Plant Room | ii. | Chillers (Water Cooled) | D/M/6M/Y | D | D | D | D |  |  | D | D | D | D | D |  |  | D | D | D | D | D |  |  | D | D | D, M | D |  |  |  | D | D | D | D
1.0 Air Conditioning and Mechanical Ventilation System | 1.1.1 Plant Room | iii. | Chillers (Air Cooled Chiller System) | D/M/6M/Y | D | D | D | D |  |  | D | D | D | D | D |  |  | D | D | D | D | D |  |  | D | D | D, M | D |  |  |  | D | D | D | D
1.0 Air Conditioning and Mechanical Ventilation System | 1.1.1 Plant Room | iv. | Pumps | M | T23: D, M
1.0 Air Conditioning and Mechanical Ventilation System | 1.1.1 Plant Room | v. | Electric Motors | M/3M | bar: T23
1.0 Air Conditioning and Mechanical Ventilation System | 1.1.1 Plant Room | vi. | Electrical Switchboard/ Control Panel | M | bar: T28
1.0 Air Conditioning and Mechanical Ventilation System | 1.1.2 Heat Exchanger Plant Room | 1.1.2 | Heat Exchanger Plant Room | M/3M | bar: T28
1.0 Air Conditioning and Mechanical Ventilation System | 1.1.3 Cooling Towers | 1.1.3 | Cooling Towers | D/M | D | D | D | D |  |  | D | D | D | D | D |  |  | D | D | D | D | D |  |  | D | D, M | D | D |  |  |  | D | D | D | D
1.0 Air Conditioning and Mechanical Ventilation System | 1.1.4 Chilled Water Storage & Expansion Tank | 1.1.4 | Chilled Water Storage & Expansion Tank | W/M/Y | bar: T04; T11; T16; T18; T28
1.0 Air Conditioning and Mechanical Ventilation System | 1.1.5 Air Handling Units and Fan-Coils | 1.1.5 | Air Handling Units and Fan-Coils | M/3M/6M/Y | bar: T16
1.0 Air Conditioning and Mechanical Ventilation System | 1.1.6 Ducting, Grilles and Dampers | 1.1.6 | Ducting, Grilles and Dampers | M/6M | bar: T16
1.0 Air Conditioning and Mechanical Ventilation System | 1.1.7 The Perfomance of The Complete Ventilation, Pressurization, Exhaust and Smoke Spill System | 1.1.7 | The Perfomance of The Complete Ventilation, Pressurization, Exhaust and Smoke Spill System | M/6M | bar: T16
1.0 Air Conditioning and Mechanical Ventilation System | 1.4.1 Evaporator (Cooling Unit) | 1.4.1 | Evaporator (Cooling Unit) | D/M/Y | D | D | D | D |  |  | D | D | D | D | D |  |  | D | D | D | D | D |  |  | D | D, M | D | D |  |  |  | D | D | D | D
1.0 Air Conditioning and Mechanical Ventilation System | 1.4.2 Condenser | 1.4.2 | Condenser | M/Y | bar: T22
1.0 Air Conditioning and Mechanical Ventilation System | 1.4.3 Electrical Switchboard / Control Panel | 1.4.3 | Electrical Switchboard / Control Panel | M | bar: T22
1.0 Air Conditioning and Mechanical Ventilation System | 1.5.1 Evaporator / Condensor | 1.5.1 | Evaporator / Condensor | M/Y | bar: T24
1.0 Air Conditioning and Mechanical Ventilation System | 1.5.2 Electrical Switchboard / Control Panel | 1.5.2 | Electrical Switchboard / Control Panel | M/Y | bar: T24
1.0 Air Conditioning and Mechanical Ventilation System | 1.6 Piping and Fittings (Expose and Accessable) | 1.6 | Piping and Fittings (Expose and Accessable) | M/6M | bar: T24
1.0 Air Conditioning and Mechanical Ventilation System | 1.7 Painting | 1.7 | Painting | Y
2.0 Fire Fighting System |  | 2.1 | General | D/6M/Y | bar: T01 to T04; T07 to T11; T14 to T18; T21 to T24; T28 to T31
2.0 Fire Fighting System | 2.2.1 Pump Room | 2.2.1 | Pump Room | W/M/6M | bar: T03; T10; T14; T17; T24; T31
2.0 Fire Fighting System | 2.2.2 Tank | 2.2.2 | Tank | W/M/6M/Y | bar: T03; T10; T14; T17; T24; T31
2.0 Fire Fighting System | 2.2.3 Pumps (General) | i. | General | M | bar: T14
2.0 Fire Fighting System | 2.2.3 Pumps (General) | ii. | Control Panel | M | bar: T14
2.0 Fire Fighting System | 2.2.4 Piping and Fittings | 2.2.4 | Piping and Fittings | M/6M | bar: T14
2.0 Fire Fighting System | 2.2.5 Landing, Valves, Hose Reel Drums, Cradles, Hoses, Nozzles, etc. | 2.2.5 | Landing, Valves, Hose Reel Drums, Cradles, Hoses, Nozzles, etc. | M | bar: T14
2.0 Fire Fighting System | 2.2.6 Sprinkler System | 2.2.6 | Sprinkler System | M | bar: T14
2.0 Fire Fighting System | 2.2.7 Breeching Inlet | 2.2.7 | Breeching Inlet | M | bar: T14
2.0 Fire Fighting System | 2.3 Fire Detection and Alarm System | 2.3 | Fire Detection and Alarm System | D/M/6M | D | D | D | D |  |  | D | D | D | D | D |  |  | D | D, M | D | D | D |  |  | D | D | D | D |  |  |  | D | D | D | D
2.0 Fire Fighting System | 2.4.1 Panel | 2.4.1 | Panel | M | bar: T15
2.0 Fire Fighting System | 2.4.2 Battery | 2.4.2 | Battery | M | bar: T15
2.0 Fire Fighting System | 2.4.3 Automatic Control | 2.4.3 | Automatic Control | M | bar: T15
2.0 Fire Fighting System | 2.4.4 Electrical | 2.4.4 | Electrical | M | bar: T15
2.0 Fire Fighting System | 2.4.5 Handsets | 2.4.5 | Handsets | M | bar: T15
2.0 Fire Fighting System | 2.4.6 General | 2.4.6 | General | M | bar: T15
2.0 Fire Fighting System | 2.5.1 Cylinder, Hoses, Canister, etc. | 2.5.1 | Cylinder, Hoses, Canister, etc. | M | bar: T15
2.0 Fire Fighting System | 2.5.2 Pilot Cylinder | 2.5.2 | Pilot Cylinder | M | bar: T15
2.0 Fire Fighting System | 2.5.3 Panel | 2.5.3 | Panel | M | bar: T15
2.0 Fire Fighting System | 2.5.4 Devices | 2.5.4 | Devices | M/3M/6M | bar: T15
2.0 Fire Fighting System | 2.5.5 Aerohub | 2.5.5 | Aerohub | M/6M | bar: T15
2.0 Fire Fighting System | 2.6 Portable Fire Extinguisher | 2.6 | Portable Fire Extinguisher | M | bar: T15
2.0 Fire Fighting System | 2.7 BOMBA Link (SPKA) | 2.7 | BOMBA Link (SPKA) | M | bar: T15
2.0 Fire Fighting System | 2.8.1 General | 2.8.1 | General | M/Y | bar: T14
2.0 Fire Fighting System | 2.8.2 Pump Room | 2.8.2 | Pump Room | M | bar: T14
2.0 Fire Fighting System | 2.8.3 Tank | 2.8.3 | Tank | M/3M/6M/Y | bar: T14
2.0 Fire Fighting System | 2.8.4 Piping and Fitting | 2.8.4 | Piping and Fitting | M | bar: T14
2.0 Fire Fighting System | 2.8.5 Pump & Motor | 2.8.5 | Pump & Motor | M | bar: T14
2.0 Fire Fighting System | 2.9 Painting | 2.9 | Painting | 6M
3.0 LIFT |  | 3.1 | Motor Room | M | bar: T09
3.0 LIFT | 3.2 Hoist Way | 3.2 | Hoist Way | M | bar: T09
3.0 LIFT | 3.3 Lift Car | 3.3 | Lift Car | M /5Y | bar: T09
3.0 LIFT | 3.4 Entrance | 3.4 | Entrance | M | bar: T09
3.0 LIFT | 3.5 Lift Pit | 3.5 | Lift Pit | M | bar: T09
3.0 LIFT | 3.6 Automatic Rescue Device (ARD) | 3.6 | Automatic Rescue Device (ARD) | M | bar: T09
3.0 LIFT | 3.7 Building Control Room | 3.7 | Building Control Room | M | bar: T09
3.0 LIFT | 3.8 VIP Lift Access System | 3.8 | VIP Lift Access System | M | bar: T09
4.0 GONDOLA |  | 4.1 | Maintenance | M | bar: T08
5.0 Cold Water Supply and Booster Pump-Pump Room |  | 5.1 | Pump room | W/M/6M | bar: T02; T09; T16 to T17; T23; T30
5.0 Cold Water Supply and Booster Pump-Pump Room | 5.2 Tanks (Suction & Storage) | 5.2 | Tanks (Suction & Storage) | M/6M | bar: T17
5.0 Cold Water Supply and Booster Pump-Pump Room | 5.3 Pumps | i. | General | M | bar: T17
5.0 Cold Water Supply and Booster Pump-Pump Room | 5.3 Pumps | ii. | Control Panel | M | bar: T17
5.0 Cold Water Supply and Booster Pump-Pump Room | 5.4 Piping & Fitting | 5.4 | Piping & Fitting | M/6M | bar: T17
5.0 Cold Water Supply and Booster Pump-Pump Room | 5.5 Pressure Vessel | 5.5 | Pressure Vessel | M | bar: T17
5.0 Cold Water Supply and Booster Pump-Pump Room | 5.6 Submersible Pumps | 5.6 | Submersible Pumps | W/M | bar: T02; T09; T16 to T17; T23; T30
5.0 Cold Water Supply and Booster Pump-Pump Room | 5.7 Painting | 5.7 | Painting | 6M
6.0 Inspection of Mechanical Services Above Ceiling |  | 6 | Inspection of Mechanical Services Above Ceiling | 6M
7.0 Kitchen Equipment |  | 7 | Kitchen Equipment | 3M
7.0 Kitchen Equipment | 7.1 Open Burner Range | 7.1 | Open Burner Range | M/3M | bar: T10
7.0 Kitchen Equipment | 7.2 Hobs | 7.2 | Hobs | M | bar: T10
7.0 Kitchen Equipment | 7.3 Kitchen Hood | 7.3 | Kitchen Hood | W/M | bar: T02; T09 to T10; T16; T23; T30
7.0 Kitchen Equipment | 7.4 Kitchen Exhaust Fan | 7.4 | Kitchen Exhaust Fan | M/6M/Y | bar: T10
8.0 Irrigation System and Landscape |  | 8.1 | Water pump | M/3M/Y | bar: T14
8.0 Irrigation System and Landscape | 8.2 Electrical Motor | 8.2 | Electrical Motor | M/3M/6M | bar: T14
8.0 Irrigation System and Landscape | 8.3 Electrical Switchboard / Control Panel | 8.3 | Electrical Switchboard / Control Panel | M/6M | bar: T14
8.0 Irrigation System and Landscape | 8.4 Piping | 8.4 | Piping | M | bar: T14
8.0 Irrigation System and Landscape | 8.5 Filter | 8.5 | Filter | M | bar: T14
8.0 Irrigation System and Landscape | 8.6 Skimmer | 8.6 | Skimmer | M | bar: T14
9.0 Other Mechanical Equipment System |  | i. | Operation | M | bar: T09
9.0 Other Mechanical Equipment System |  | ii. | Maintenance | M | bar: T09
9.0 Other Mechanical Equipment System | 9.1 Roller Shutter / Fire Roller Shutter | i. | General | M | bar: T09
9.0 Other Mechanical Equipment System | 9.1 Roller Shutter / Fire Roller Shutter | ii. | Electric Motors | M | bar: T09
9.0 Other Mechanical Equipment System | 9.1 Roller Shutter / Fire Roller Shutter | iii. | Electrical Switchboard / Control Panel | M | bar: T09
9.0 Other Mechanical Equipment System | 9.2 Hand Dryer | 9.2 | Hand Dryer | W/M | bar: T01; T07; T09; T14; T21; T28
9.0 Other Mechanical Equipment System | 9.3 Grey Water Harvesting System | i. | General | W/M | bar: T01; T07; T09; T14; T21; T28
9.0 Other Mechanical Equipment System | 9.4 Rain Water Harvesting System | i. | General | W/M | bar: T01; T07; T09; T14; T21; T28
9.0 Other Mechanical Equipment System | 9.4 Rain Water Harvesting System | ii. | Control Panel | M | bar: T09